## Actions
Action # | Committee | Subgroup (Leave blank if not relevant) | Outcome | Action | Sub-Action (Leave blank if not relevant) | Description | Parties Responsible | Tangible/Intangible | Team Project Manager | Initial Target Delivery Date | Endorsed by Mayor | Progress | Count | Key/Standard
1 | Business, Workforce & Neighborhood Development | Business Subgroup | Stabilize and Position Small Businesses for Growth | Build Small Business Access to Capital | Target at least 50% of BDC’s grants on small and minority business growth | TBD | Mayor; BDC | Tangible | TBD | 2021-02-01 | TBD | In progress | 1 | Key
2 | Business, Workforce & Neighborhood Development | Business Subgroup | Stabilize and Position Small Businesses for Growth | Build Small Business Access to Capital | Create a Rapid Pay Program that pays small businesses within 2-weeks | TBD | Mayor; BAPS; CitiStat | Tangible | TBD | 2021-02-01 | TBD | Not yet started | 1 | Standard
3 | Business, Workforce & Neighborhood Development | Business Subgroup | Stabilize and Position Small Businesses for Growth | Build Small Business Access to Capital | Provide credit support to Community Development Financial Institutions, or CDFIs. to provide loans, grants, equity and technical assistance | TBD | Mayor; CDFIs; BDC | Tangible | TBD | 2021-02-01 | TBD | Not yet started | 1 | Key
4 | Business, Workforce & Neighborhood Development | Business Subgroup | Stabilize and Position Small Businesses for Growth | Build Small Business Access to Capital | Create Capital Pools / Create a $50M Small Business Fund (Call on the foundations) | TBD | Mayor; Finance; Foundations | Tangible | TBD | 2021-02-01 | TBD | Not yet started | 1 | Standard
5 | Business, Workforce & Neighborhood Development | Business Subgroup | Stabilize and Position Small Businesses for Growth | Small/Local Preference | Add small/local preference points to the procurement process | TBD | Mayor; Finance; Procurement | Tangible | TBD | 2021-02-01 | TBD | Not yet started | 1 | Standard
6 | Business, Workforce & Neighborhood Development | Business Subgroup | Stabilize and Position Small Businesses for Growth | Small/Local Preference | Provide incentive for businesses who hire local | TBD | Mayor; Finance; Procurement | Tangible | TBD | 2021-02-01 | TBD | Not yet started | 1 | Standard
7 | Business, Workforce & Neighborhood Development | Business Subgroup | Stabilize and Position Small Businesses for Growth | Small/Local Preference | Create local vendor preference list | TBD | Mayor; Finance; Procurement | Tangible | TBD | 2021-02-01 | TBD | Not yet started | 1 | Key
8 | Business, Workforce & Neighborhood Development | Business Subgroup | Stabilize and Position Small Businesses for Growth | Restaurant Recovery | Prioritize Cares Act funding to small/minority-owned restaurants | TBD | Mayor; Finance | Tangible | TBD | 2021-02-02 | TBD | Not yet started | 1 | Standard
9 | Business, Workforce & Neighborhood Development | Business Subgroup | Stabilize and Position Small Businesses for Growth | Restaurant Recovery | Cap restaurant delivery fees on third-party app services like Uber Eats/GrubHub, etc | TBD | Mayor; Finance; City Council | Tangible | TBD | 2021-02-03 | TBD | Not yet started | 1 | Key
10 | Business, Workforce & Neighborhood Development | Business Subgroup | Stabilize and Position Small Businesses for Growth | Reimagine/Establish an Authentic yet Aspirational Baltimore Story | Create a Mission/Marketing Message - What do we stand for/aspire to? (Residents/Businesses want to feel like they are a part of something) | TBD | Mayor | Intangible | TBD | 2021-02-04 | TBD | Not yet started | 1 | Standard
11 | Business, Workforce & Neighborhood Development | Business Subgroup | Establish the position that this is a Progressive Administration that is open for business | Prioritize Clean and Safe physically and in the messaging | Position the city as the Mecca for Small Business and Entrepreneurship | TBD | Mayor | Intangible | TBD | 2021-02-05 | TBD | Not yet started | 1 | Standard
12 | Business, Workforce & Neighborhood Development | Business Subgroup | Demonstrate that Baltimore is Committed to Retention and Attraction of the Business Community | Create the role of an Ombudsman for Business within the Mayor’s Office |  | TBD | Mayor | Tangible | TBD | 2021-02-06 | TBD | Not yet started | 1 | Standard
13 | Business, Workforce & Neighborhood Development | Business Subgroup | Demonstrate that Baltimore is Committed to Retention and Attraction of the Business Community | Establish tax incentives for small and large businesses |  | TBD | Mayor | Tangible | TBD | 2021-02-07 | TBD | Not yet started | 1 | Key
14 | Business, Workforce & Neighborhood Development | Business Subgroup | Demonstrate that Baltimore is Committed to Retention and Attraction of the Business Community | Develop an attraction strategy to fill vacant office space/street-level retail |  | TBD | Mayor | Intangible | TBD | 2021-02-08 | TBD | Not yet started | 1 | Standard
15 | Business, Workforce & Neighborhood Development | Business Subgroup | Demonstrate that Baltimore is Committed to Retention and Attraction of the Business Community | Focus on developing a small business ecosystem |  | TBD | Mayor | Intangible | TBD | 2021-02-09 | TBD | Not yet started | 1 | Key
16 | Business, Workforce & Neighborhood Development | Business Subgroup | Demonstrate that Baltimore is Committed to Retention and Attraction of the Business Community | Establish a task force to evaluate signature development opportunities that include opportunities for local investment |  | TBD | Mayor | Intangible | TBD | 2021-02-10 | TBD | Not yet started | 1 | Standard
17 | Business, Workforce & Neighborhood Development | Neighborhood Subgroup | Revitalize Neighborhoods by creating an accountability matrix and cross communication amongst neighborhood leaders | Implement a model at community level to give community a direct voice |  | TBD | Mayor | Tangible | TBD | 2021-02-11 | TBD | Not yet started | 1 | Standard
18 | Business, Workforce & Neighborhood Development | Neighborhood Subgroup | Revitalize Neighborhoods by creating an accountability matrix and cross communication amongst neighborhood leaders | Establish committee of neighborhood leaders by district |  | TBD | Mayor | Tangible | TBD | 2021-02-12 | TBD | Not yet started | 1 | Standard
19 | Business, Workforce & Neighborhood Development | Neighborhood Subgroup | Revitalize Neighborhoods by creating an accountability matrix and cross communication amongst neighborhood leaders | Create communications between City Departments that allow City Developments to move forward in a timely manner |  | TBD | Mayor | Tangible | TBD | 2021-02-13 | TBD | Not yet started | 1 | Key
20 | Business, Workforce & Neighborhood Development | Neighborhood Subgroup | Tax Credits, Incentives, & Payment Options for homeowners | Provide payment plans or early payment credits for home taxes so revenue can be used to assist local developers |  | TBD | Mayor | Tangible | TBD | 2021-02-14 | TBD | Not yet started | 1 | Standard
21 | Business, Workforce & Neighborhood Development | Neighborhood Subgroup | Tax Credits, Incentives, & Payment Options for homeowners | Provide tax breaks for local developers that create value in neighborhoods designated as opportunity zones |  | TBD | Mayor | Tangible | TBD | 2021-02-15 | TBD | Not yet started | 1 | Key
22 | Business, Workforce & Neighborhood Development | Neighborhood Subgroup | Tax Credits, Incentives, & Payment Options for homeowners | Relieve/reform processes for acquiring vacant homes (including those with liens) and tax sale for owner occupancies to reduce and eventually eliminate blight |  | TBD | Mayor | Tangible | TBD | 2021-02-16 | TBD | Not yet started | 1 | Standard
23 | Business, Workforce & Neighborhood Development | Neighborhood Subgroup | CDFI ‘s as funding to support Tax Incentives | Provide local support to CDFIs to provide funding to small developers and revitalize neighborhoods. |  | TBD | Mayor | Tangible | TBD | 2021-02-17 | TBD | Not yet started | 1 | Standard
24 | Business, Workforce & Neighborhood Development | Neighborhood Subgroup | Prioritize building and redeveloping greenspaces in urban areas that promote neighborhood revitalization, stabilization, and re-investments | Define what are the needs of parks and green spaces in urban communities |  | TBD | Mayor | Tangible | TBD | 2021-02-18 | TBD | Not yet started | 1 | Standard
25 | Business, Workforce & Neighborhood Development | Neighborhood Subgroup | Prioritize building and redeveloping greenspaces in urban areas that promote neighborhood revitalization, stabilization, and re-investments | Identify and document stakeholders as community leaders, stakeholders, and prominent community voices |  | TBD | Mayor | Tangible | TBD | 2021-02-19 | TBD | Not yet started | 1 | Key
26 | Business, Workforce & Neighborhood Development | Neighborhood Subgroup | Prioritize building and redeveloping greenspaces in urban areas that promote neighborhood revitalization, stabilization, and re-investments | Communicate with council leaders in districts to Identify priority areas and to review the prioritization of greenspaces in their corridor plans |  | TBD | Mayor | Tangible | TBD | 2021-02-20 | TBD | Not yet started | 1 | Standard
27 | Transportation & Infrastructure |  | Adopt and Support the Complete Streets Manual | Work with the City Council to adopt the final draft of the Complete Streets Manual. Publicly issuing support will empower the agency to enact the positive changes in the manual. It is currently in its final draft phase and its policies will go into effect as soon as it receives approval from the City Council and the Mayor. This will fulfill requirements laid out in the Complete Streets Ordinance. | [7 empty] | Not yet started | 1 | Standard
28 | Transportation & Infrastructure |  | Demonstrate Commitment to Equity | Initiate a Fix-it First campaign to fill the backlog of transportation and infrastructure related 311 service requests (potholes, sidewalk repairs, crosswalk markings, damaged street lights, leaking water mains) in areas where the City has typically had a longer response time (Black Butterfly neighborhoods, etc.). This was done via CleanStat for DPW related 311 SRs, but the public facing DOTStat is not up and running yet. The campaign could be similar to DC's Potholepalooza, but more expansive while demonstrating progress on Mayor-elect Scott's vision for equity. | [7 empty] | Not yet started | 1 | Standard
29 | Transportation & Infrastructure |  | Demonstrate Commitment to Equity | Release the Water Billing report from Spring 2020 to the public. | [7 empty] | Not yet started | 1 | Standard
30 | Transportation & Infrastructure |  | Demonstrate Commitment to Equity | Coordinate with the Comptroller's Office to complete an audit of the water billing system. | [7 empty] | Not yet started | 1 | Standard
31 | Transportation & Infrastructure |  | Demonstrate Commitment to Equity | Begin implementation of the Water Accountability and Equity Act which discounts water bills based on income. | [7 empty] | Not yet started | 1 | Standard
32 | Transportation & Infrastructure |  | Plan for the Future | Pledge to prioritize the Baltimore Greenway Trails Network. This economic development and capital improvement project is currently being developed in collaboration between the Department of Planning, Department of Transportation, and Department of Recreation and Parks, and is receiving wide ranging community support. Pledging your commitment, and tasking a key official with leadership of this effort, would provide the necessary political will that will move the project forward and position it to be a transformational project delivered in the next four years. Decisions like negotiating with Norfolk Southern to purchase an abandoned rail corridor that could be converted into trails can only happen with the Mayor’s support. | [7 empty] | Not yet started | 1 | Standard
33 | Transportation & Infrastructure |  | Plan for the Future | Develop a robust legislative agenda for the 2021 General Assembly session, identify City Delegation sponsors, and pre-file legislation that gives the City more autonomy over its transportation revenue and treatments. Specifically, support the Transit Safety & Investment Act to require that the Maryland Department of Transportation provide at least a minimum amount of funding needed for the Maryland Transit Administration to maintain existing infrastructure and provide safe, reliable service. | [7 empty] | Not yet started | 1 | Standard
34 | Transportation & Infrastructure |  | Plan for the Future | Support green infrastructure and incorporate sustainability measures into routine maintenance. Invest in materials that improve stormwater management such as permeable concrete and reduce the heat island effect. | [7 empty] | Not yet started | 1 | Standard
35 | Transportation & Infrastructure |  | Plan for the Future | Meet with surrounding county leadership such as County Executives to gain support for a transportation/transit plan that provides access to jobs throughout the Greater Baltimore Region. | [7 empty] | Not yet started | 1 | Standard
36 | Transportation & Infrastructure |  | Plan for the Future | Appoint senior DOT staff to participate on the Regional Transit Plan Implementation Team to advance the 2 early priority corridors that would serve Baltimore City. | [7 empty] | Not yet started | 1 | Standard
37 | Transportation & Infrastructure |  | Leadership | Appoint a Deputy Mayor (or similar position) for transportation and public works that can coordinate multiple agency heads to deliver projects and advise the mayor’s team. Ideally this person would be an executive with national transportation and public works experience and a visionary approach to complete streets, transit, and trail infrastructure. The Department of Transportation has a responsibility to design and build changes to the roadway that improve safety but often face budget constraints that prohibit projects from being completed in a timely manner. Capital dollars exist in the Department of Public Works budget for utility work. Repaving the road following a Department of Public Works improvement project provides a cost effective opportunity to improve design. A Deputy Mayor would require agencies to coordinate paving projects to improve efficiency and reduce costs of Complete Streets projects like repainting crosswalks. | [7 empty] | Not yet started | 1 | Standard
38 | Transportation & Infrastructure |  | Leadership | Additionally, hire change agents to fill the Deputy Director of Complete Streets, Transit Chief, and Traffic Chief positions. | [7 empty] | Not yet started | 1 | Standard
39 | Transportation & Infrastructure |  | Improving the safety of vulnerable road users | Change our standard ADA curb cut retrofit to a design that promotes traffic calming and has dedicated ramps to each crosswalk instead of on the turn radius. Baltimore has one of the largest percentages of populations that rely on a mobility device. The current curb cut standard requires those with a lower vantage point to go out into the travel lane to access the crosswalk. A simple policy change and adoption of a new design standard would mean that moving forward, new crosswalk curb cuts would better accommodate road users using a mobility device or pushing a stroller. | [7 empty] | Not yet started | 1 | Standard
40 | Transportation & Infrastructure |  | Improving the safety of vulnerable road users | Remove beg buttons from our specifications on crosswalk enhancements and implement default pedestrian crossing on all signals, prioritizing implementation at trail crossings, hospitals, grocery stores, park access, and other equity priority areas. Ending the use of beg buttons in the new crosswalk design would make new signaled crosswalks cost less. It would also mean people don’t have to touch a button other people have used. It would improve safety by providing a crossing signal automatically. | [7 empty] | Not yet started | 1 | Standard
41 | Transportation & Infrastructure |  | Improving the safety of vulnerable road users | Prioritize ADA retrofit within 1⁄2 mile of transit stops, followed by senior centers/housing, grocery stores, healthcare facilities, parks, and other equity priority areas. These changes in ADA design will not happen overnight. But endorsing these policies mean that all future projects will be less expensive and safer for everyone. | [7 empty] | Not yet started | 1 | Standard
42 | Transportation & Infrastructure |  | Improving the safety of vulnerable road users | Approve MTA permits so contractors can repaint bus lanes, and work with MTA to enforce bus lanes. | [7 empty] | Not yet started | 1 | Standard
43 | [11 empty] | Not yet started | 1
44 | [11 empty] | Not yet started | 1
45 | [11 empty] | Not yet started | 1
46 | [11 empty] | Not yet started | 1
47 | [11 empty] | Not yet started | 1
48 | [11 empty] | Not yet started | 1
49 | [11 empty] | Not yet started | 1
50 | [11 empty] | Not yet started | 1

## Days
2021 First 100 Days Number | Mayoral First 100 Days Number | Date | Weekday | Milestone? | Notes?
| 1 | 2020-12-08 | 2020-12-08 | Mayor Scott Inauguration
| 2 | 2020-12-09 | 2020-12-09
| 3 | 2020-12-10 | 2020-12-10
| 4 | 2020-12-11 | 2020-12-11
| 5 | 2020-12-12 | 2020-12-12
| 6 | 2020-12-13 | 2020-12-13
| 7 | 2020-12-14 | 2020-12-14
| 8 | 2020-12-15 | 2020-12-15
| 9 | 2020-12-16 | 2020-12-16
| 10 | 2020-12-17 | 2020-12-17
| 11 | 2020-12-18 | 2020-12-18
| 12 | 2020-12-19 | 2020-12-19
| 13 | 2020-12-20 | 2020-12-20
| 14 | 2020-12-21 | 2020-12-21
| 15 | 2020-12-22 | 2020-12-22
| 16 | 2020-12-23 | 2020-12-23
| 17 | 2020-12-24 | 2020-12-24
| 18 | 2020-12-25 | 2020-12-25
| 19 | 2020-12-26 | 2020-12-26
| 20 | 2020-12-27 | 2020-12-27
| 21 | 2020-12-28 | 2020-12-28
| 22 | 2020-12-29 | 2020-12-29
| 23 | 2020-12-30 | 2020-12-30
| 24 | 2020-12-31 | 2020-12-31
1 | 25 | 2021-01-01 | 2021-01-01 | First quarter ends
2 | 26 | 2021-01-02 | 2021-01-02
3 | 27 | 2021-01-03 | 2021-01-03
4 | 28 | 2021-01-04 | 2021-01-04
5 | 29 | 2021-01-05 | 2021-01-05
6 | 30 | 2021-01-06 | 2021-01-06
7 | 31 | 2021-01-07 | 2021-01-07
8 | 32 | 2021-01-08 | 2021-01-08
9 | 33 | 2021-01-09 | 2021-01-09
10 | 34 | 2021-01-10 | 2021-01-10
11 | 35 | 2021-01-11 | 2021-01-11
12 | 36 | 2021-01-12 | 2021-01-12
13 | 37 | 2021-01-13 | 2021-01-13
14 | 38 | 2021-01-14 | 2021-01-14
15 | 39 | 2021-01-15 | 2021-01-15
16 | 40 | 2021-01-16 | 2021-01-16
17 | 41 | 2021-01-17 | 2021-01-17
18 | 42 | 2021-01-18 | 2021-01-18
19 | 43 | 2021-01-19 | 2021-01-19
20 | 44 | 2021-01-20 | 2021-01-20
21 | 45 | 2021-01-21 | 2021-01-21
22 | 46 | 2021-01-22 | 2021-01-22
23 | 47 | 2021-01-23 | 2021-01-23
24 | 48 | 2021-01-24 | 2021-01-24
25 | 49 | 2021-01-25 | 2021-01-25
26 | 50 | 2021-01-26 | 2021-01-26 | First half ends
27 | 51 | 2021-01-27 | 2021-01-27
28 | 52 | 2021-01-28 | 2021-01-28
29 | 53 | 2021-01-29 | 2021-01-29
30 | 54 | 2021-01-30 | 2021-01-30
31 | 55 | 2021-01-31 | 2021-01-31
32 | 56 | 2021-02-01 | 2021-02-01
33 | 57 | 2021-02-02 | 2021-02-02
34 | 58 | 2021-02-03 | 2021-02-03
35 | 59 | 2021-02-04 | 2021-02-04
36 | 60 | 2021-02-05 | 2021-02-05
37 | 61 | 2021-02-06 | 2021-02-06
38 | 62 | 2021-02-07 | 2021-02-07
39 | 63 | 2021-02-08 | 2021-02-08
40 | 64 | 2021-02-09 | 2021-02-09
41 | 65 | 2021-02-10 | 2021-02-10
42 | 66 | 2021-02-11 | 2021-02-11
43 | 67 | 2021-02-12 | 2021-02-12
44 | 68 | 2021-02-13 | 2021-02-13
45 | 69 | 2021-02-14 | 2021-02-14
46 | 70 | 2021-02-15 | 2021-02-15
47 | 71 | 2021-02-16 | 2021-02-16
48 | 72 | 2021-02-17 | 2021-02-17
49 | 73 | 2021-02-18 | 2021-02-18
50 | 74 | 2021-02-19 | 2021-02-19
51 | 75 | 2021-02-20 | 2021-02-20 | Third quarter ends
52 | 76 | 2021-02-21 | 2021-02-21
53 | 77 | 2021-02-22 | 2021-02-22
54 | 78 | 2021-02-23 | 2021-02-23
55 | 79 | 2021-02-24 | 2021-02-24
56 | 80 | 2021-02-25 | 2021-02-25
57 | 81 | 2021-02-26 | 2021-02-26
58 | 82 | 2021-02-27 | 2021-02-27
59 | 83 | 2021-02-28 | 2021-02-28
60 | 84 | 2021-03-01 | 2021-03-01
61 | 85 | 2021-03-02 | 2021-03-02
62 | 86 | 2021-03-03 | 2021-03-03
63 | 87 | 2021-03-04 | 2021-03-04
64 | 88 | 2021-03-05 | 2021-03-05
65 | 89 | 2021-03-06 | 2021-03-06
66 | 90 | 2021-03-07 | 2021-03-07
67 | 91 | 2021-03-08 | 2021-03-08
68 | 92 | 2021-03-09 | 2021-03-09
69 | 93 | 2021-03-10 | 2021-03-10
70 | 94 | 2021-03-11 | 2021-03-11
71 | 95 | 2021-03-12 | 2021-03-12
72 | 96 | 2021-03-13 | 2021-03-13
73 | 97 | 2021-03-14 | 2021-03-14
74 | 98 | 2021-03-15 | 2021-03-15
75 | 99 | 2021-03-16 | 2021-03-16
76 | 100 | 2021-03-17 | 2021-03-17 | End of first 100 days
77 |  | 2021-03-18 | 2021-03-18
78 |  | 2021-03-19 | 2021-03-19
79 |  | 2021-03-20 | 2021-03-20
80 |  | 2021-03-21 | 2021-03-21
81 |  | 2021-03-22 | 2021-03-22
82 |  | 2021-03-23 | 2021-03-23
83 |  | 2021-03-24 | 2021-03-24
84 |  | 2021-03-25 | 2021-03-25
85 |  | 2021-03-26 | 2021-03-26
86 |  | 2021-03-27 | 2021-03-27
87 |  | 2021-03-28 | 2021-03-28
88 |  | 2021-03-29 | 2021-03-29
89 |  | 2021-03-30 | 2021-03-30
90 |  | 2021-03-31 | 2021-03-31
91 |  | 2021-04-01 | 2021-04-01
92 |  | 2021-04-02 | 2021-04-02
93 |  | 2021-04-03 | 2021-04-03
94 |  | 2021-04-04 | 2021-04-04
95 |  | 2021-04-05 | 2021-04-05
96 |  | 2021-04-06 | 2021-04-06
97 |  | 2021-04-07 | 2021-04-07
98 |  | 2021-04-08 | 2021-04-08
99 |  | 2021-04-09 | 2021-04-09
100 |  | 2021-04-10 | 2021-04-10
Formulas:
Weekday = [Date]

## Committees
Number | Name | Priority | Icon 1 | Icon 2
1 | Public Health & Public Safety | Reimagining Public Safety and Public Accountability
2 | Business, Workforce & Neighborhood Development | Strengthening Neighborhoods and Businesses
3 | Fiscal Preparedness | Aligning Resources to Ensure Fiscal Stability and Innovation
4 | Education & Youth Recreation | Expanding Opportunities for Youth
5 | Housing & Neighborhood Development | Increasing Access to Affordable Housing
6 | Transportation & Infrastructure | Reinvigorating Our Transportation and Infrastructure
7 | Human Services | Prioritizing Our People
8 | Governance Structure & Operations | Rethinking Governmental Operations
9 | Environment & Sustainability | Protecting Natural Resources
10 | Arts & Culture | Valuing Creative Hubs and Cultural Institutions

## Progress Updates
Action # | Action | Date of Update | Description of Update | Status
1 | Business, Workforce & Neighborhood Development | 2020-12-14 | DPW is determining a date to re-launch recycling services. | In progress

## Notes
This spreadsheet is designed to assist the Mayor's Office with tracking the set of short-term actions that it aims to accomplish within the first 100 days of Mayor Scott's term.
The Mayor's transition team has communicated to OPI that each of the 10 transition committees have been tasked with identifying 3-5 short-term actions to be accomplished within the first 100 days of the term. This means that in total, the committees will be identifying between 30-50 actions. Mayor Scott and his team will review this list and pare it down.
For each action, the following things should be determined:
Responsibility for completion of the action
Responsibility for communication of updates to the Mayor's team (and OPI for the purposes of the tracker)
Definition for what constitutes completion of the action
Project Timeline/Title:
100 Days of Action
Year 1 Agenda

## Possible Statuses
Status | Percentage
Incomplete
Complete