## Actions
Action # | Committee | Action | Description | Parties Responsible | Tangible/Intangible | Team Project Manager | Initial Target Delivery Date | Endorsed by Mayor | Progress | Count | Key/Standard
1 | Building Public Safety | Create Mayor's Office of Neighborhood Safety and Engagement. |  | Mayor's Office of Neighborhood Safety & Engagement | Tangible | TBD | 2021-02-01 | TBD | Complete | 1 | Key
2 | Building Public Safety | Establish monthly PoliceStat meetings to build stronger accountability within BPD and improve service delivery. |  | Baltimore Police Department | Tangible | TBD | 2021-02-01 | TBD | Complete | 1 | Standard
3 | Building Public Safety | Set clear, coordinated public safety vision that addresses violence today and root causes. |  | Mayor's Office, Mayor's Office of Neighborhood Safety and Engagement, Baltimore City Health Department, & Baltimore Police Department | Tangible | TBD | 2021-02-01 | TBD | In Progress | 1 | Key
4 | Building Public Safety | Task Mayor's Office of Neighborhood Safety and Engagement with coordinating public safety strategy. |  | Mayor's Office of Neighborhood Safety & Engagement | Tangible | TBD | 2021-02-01 | TBD | In Progress | 1 | Standard
5 | Building Public Safety | Introduce local housing voucher program. |  | Department of Housing & Community Development | Tangible | TBD | 2021-02-01 | TBD | Not Yet Started | 1 | Standard
6 | Building Public Safety | Adopt and support Complete Streets manual increase quality of life and mobility in Baltimore. |  | Department of Transportation | Tangible | TBD | 2021-02-01 | TBD | Not Yet Started | 1 | Standard
7 | Making Baltimore Equitable | Hire Baltimore's first Chief Equity Officer. |  | Mayor's Office & Office of Equity and Civil Rights | Tangible | TBD | 2021-02-01 | TBD | Complete | 1 | Key
8 | Making Baltimore Equitable | Identify a senior official in each agency to be responsible for equity and sustainable action. |  | Mayor's Office | Tangible | TBD | 2021-02-02 | TBD | In Progress | 1 | Standard
9 | Making Baltimore Equitable | Commit to Baltimore's zero waste goals and begin shifts toward a more sustainable city. |  | Mayor's Office & Department of Planning | Tangible | TBD | 2021-02-03 | TBD | Not Yet Started | 1 | Key
10 | Making Baltimore Equitable | Elevate Sustainability Director to a cabinet-level position. |  | Mayor's Office & Department of Planning | Intangible | TBD | 2021-02-04 | TBD | Not Yet Started | 1 | Standard
11 | Making Baltimore Equitable | Remove the most vulnerable residents from tax sale. |  | Department of Finance | Intangible | TBD | 2021-02-05 | TBD | Not Yet Started | 1 | Standard
12 | Making Baltimore Equitable | Announce a back-to-basics community development strategy that centers community input. |  | Mayor's Office & Department of Housing & Community Development | Tangible | TBD | 2021-02-06 | TBD | Not Yet Started | 1 | Standard
13 | Making Baltimore Equitable | Activate small and local business preference in the procurement process. |  | Department of Finance, Bureau of Procurement | Tangible | TBD | 2021-02-07 | TBD | Not Yet Started | 1 | Key
14 | Making Baltimore Equitable | Prioritize the Baltimore Greenway Trails Network. |  | Department of Planning, Department of Transportation, Baltimore City Recreation & Parks | Intangible | TBD | 2021-02-08 | TBD | Not Yet Started | 1 | Standard
15 | Prioritizing Our Youth | Support the overrides of the Blueprint for Maryland's Future and Built to Learn. |  | Mayor's Office & Maryland General Assembly | Intangible | TBD | 2021-02-09 | TBD | Not Yet Started | 1 | Key
16 | Prioritizing Our Youth | Prepare to significantly increase the capacity of virtual YouthWorks in 2021. |  | Mayor's Office of Employment Development | Intangible | TBD | 2021-02-10 | TBD | Not Yet Started | 1 | Standard
17 | Prioritizing Our Youth | Begin implementation and allocate funding to the Elijah Cummings Healing City Act to ensure trauma-informed practice. |  | Baltimore City Housing Department & Mayor's Office of Neighborhood Safety & Engagement | Tangible | TBD | 2021-02-11 | TBD | Not Yet Started | 1 | Standard
18 | Prioritizing Our Youth | Develop plan for equitable and age-appropriate access in partnership with sports, arts, and cultural institutions that create recreational services during this unprecedented pandemic. |  | Baltimore City Recreation & Parks | Tangible | TBD | 2021-02-12 | TBD | Not Yet Started | 1 | Standard
19 | Building Public Trust | Hire Baltimore's first Chief Administrative Officer. |  | Mayor's Office | Tangible | TBD | 2021-02-13 | TBD | Complete | 1 | Key
20 | Building Public Trust | Kick off community engagement plan to introduce Chief Administrative Officer and other senior officials to public. |  | Mayor's Office | Tangible | TBD | 2021-02-14 | TBD | In Progress | 1 | Standard
21 | Building Public Trust | Establish a regular Stat program to ensure greater accountability and more equitable service delivery across City government. |  | Office of Performance & Innovation | Tangible | TBD | 2021-02-15 | TBD | Not Yet Started | 1 | Key
22 | Building Public Trust | Restore recycling services, which were suspended due to COVID-19. |  | Department of Public Works | Tangible | TBD | 2021-02-16 | TBD | Not Yet Started | 1 | Standard
23 | Building Public Trust | Announce plan to reform the water billing program. |  | Department of Public Works | Tangible | TBD | 2021-02-17 | TBD | Not Yet Started | 1 | Standard
24 | Building Public Trust | Appoint a permanent Housing Commissioner. |  | Department of Housing & Community Development | Tangible | TBD | 2021-02-18 | TBD | Not Yet Started | 1 | Standard
25 | Building Public Trust | Appoint a permanent Homeless Services director. |  | Mayor's Office of Homeless Services | Tangible | TBD | 2021-02-19 | TBD | Not Yet Started | 1 | Key
26 | Building Public Trust | Initiate a Fix-it First campaign to fill backlog of transportation and infrastructure related 311 service requests, particularly where there has historically been a longer response time. |  | Department of Public Works & Department of Transportation | Tangible | TBD | 2021-02-20 | TBD | Not Yet Started | 1 | Standard
27 | Building Public Trust | Make stronger commitments to cleaning up sewage backups. |  | Department of Public Works |  |  |  |  | Not Yet Started | 1 | Standard
28 | COVID-19 Recovery | Develop and communicate a COVID-19 vaccination prioritization strategy. |  | Baltimore City Health Department |  |  |  |  | Not Yet Started | 1 | Standard
29 | COVID-19 Recovery | Create a dashboard to track CARES act funding to ensure equitable distribution. |  | Department of Finance |  |  |  |  | Not Yet Started | 1 | Standard
30 | COVID-19 Recovery | Use Rapid Rehousing CARES Act dollars to move 500 people and families to more permanent housing. |  | Mayor's Office of Homeless Services |  |  |  |  | Not Yet Started | 1 | Standard
31 | COVID-19 Recovery | Extend emergency shelter in local hotels when CARES Act funding expires. |  | Mayor's Office of Homeless Services |  |  |  |  | Not Yet Started | 1 | Standard
32 | COVID-19 Recovery | Cap restaurant delivery fees on third-party app services. |  | Department of Finance |  |  |  |  | In Progress | 1 | Standard
33 | COVID-19 Recovery | Identify clear point of contact for local businesses to more effectively navigate city government. |  | Mayor's Office & Baltimore Development Corporation |  |  |  |  | Not Yet Started | 1 | Standard
34 | Responsible Stewardship of City Resources | Begin holistic, top-to-bottom assessment of city agencies and process to inventory city property. |  | Department of General Services |  |  |  |  | Not Yet Started | 1 | Standard
35 | Responsible Stewardship of City Resources | Begin a holistic review of tax credits to address inefficiencies, redundancies, or new credits that would build a more equitable city. |  | Department of Finance |  |  |  |  | Not Yet Started | 1 | Standard
36 | Responsible Stewardship of City Resources | Announce new criteria for evaluation of capital budget requests. |  | Mayor's Office & Department of Finance |  |  |  |  | Not Yet Started | 1 | Standard
37 | Responsible Stewardship of City Resources | Design and release Open Checkbook for Baltimore to increase transparency and accountability. |  | Department of Finance & Baltimore City IT |  |  |  |  | Not Yet Started | 1 | Standard
Note on A1: Please do not edit this column. This will update programmatically based on data in the Progress Updates tab. -Brendan Hellweg

## Days
2021 First 100 Days Number | Mayoral First 100 Days Number | Date | Weekday | Milestone? | Notes?
| 1 | 2020-12-08 | 2020-12-08 | Mayor Scott Inauguration
| 2 | 2020-12-09 | 2020-12-09
| 3 | 2020-12-10 | 2020-12-10
| 4 | 2020-12-11 | 2020-12-11
| 5 | 2020-12-12 | 2020-12-12
| 6 | 2020-12-13 | 2020-12-13
| 7 | 2020-12-14 | 2020-12-14
| 8 | 2020-12-15 | 2020-12-15
| 9 | 2020-12-16 | 2020-12-16
| 10 | 2020-12-17 | 2020-12-17
| 11 | 2020-12-18 | 2020-12-18
| 12 | 2020-12-19 | 2020-12-19
| 13 | 2020-12-20 | 2020-12-20
| 14 | 2020-12-21 | 2020-12-21
| 15 | 2020-12-22 | 2020-12-22
| 16 | 2020-12-23 | 2020-12-23
| 17 | 2020-12-24 | 2020-12-24
| 18 | 2020-12-25 | 2020-12-25
| 19 | 2020-12-26 | 2020-12-26
| 20 | 2020-12-27 | 2020-12-27
| 21 | 2020-12-28 | 2020-12-28
| 22 | 2020-12-29 | 2020-12-29
| 23 | 2020-12-30 | 2020-12-30
| 24 | 2020-12-31 | 2020-12-31
1 | 25 | 2021-01-01 | 2021-01-01 | First quarter ends
2 | 26 | 2021-01-02 | 2021-01-02
3 | 27 | 2021-01-03 | 2021-01-03
4 | 28 | 2021-01-04 | 2021-01-04
5 | 29 | 2021-01-05 | 2021-01-05
6 | 30 | 2021-01-06 | 2021-01-06
7 | 31 | 2021-01-07 | 2021-01-07
8 | 32 | 2021-01-08 | 2021-01-08
9 | 33 | 2021-01-09 | 2021-01-09
10 | 34 | 2021-01-10 | 2021-01-10
11 | 35 | 2021-01-11 | 2021-01-11
12 | 36 | 2021-01-12 | 2021-01-12
13 | 37 | 2021-01-13 | 2021-01-13
14 | 38 | 2021-01-14 | 2021-01-14
15 | 39 | 2021-01-15 | 2021-01-15
16 | 40 | 2021-01-16 | 2021-01-16
17 | 41 | 2021-01-17 | 2021-01-17
18 | 42 | 2021-01-18 | 2021-01-18
19 | 43 | 2021-01-19 | 2021-01-19
20 | 44 | 2021-01-20 | 2021-01-20
21 | 45 | 2021-01-21 | 2021-01-21
22 | 46 | 2021-01-22 | 2021-01-22
23 | 47 | 2021-01-23 | 2021-01-23
24 | 48 | 2021-01-24 | 2021-01-24
25 | 49 | 2021-01-25 | 2021-01-25
26 | 50 | 2021-01-26 | 2021-01-26 | First half ends
27 | 51 | 2021-01-27 | 2021-01-27
28 | 52 | 2021-01-28 | 2021-01-28
29 | 53 | 2021-01-29 | 2021-01-29
30 | 54 | 2021-01-30 | 2021-01-30
31 | 55 | 2021-01-31 | 2021-01-31
32 | 56 | 2021-02-01 | 2021-02-01
33 | 57 | 2021-02-02 | 2021-02-02
34 | 58 | 2021-02-03 | 2021-02-03
35 | 59 | 2021-02-04 | 2021-02-04
36 | 60 | 2021-02-05 | 2021-02-05
37 | 61 | 2021-02-06 | 2021-02-06
38 | 62 | 2021-02-07 | 2021-02-07
39 | 63 | 2021-02-08 | 2021-02-08
40 | 64 | 2021-02-09 | 2021-02-09
41 | 65 | 2021-02-10 | 2021-02-10
42 | 66 | 2021-02-11 | 2021-02-11
43 | 67 | 2021-02-12 | 2021-02-12
44 | 68 | 2021-02-13 | 2021-02-13
45 | 69 | 2021-02-14 | 2021-02-14
46 | 70 | 2021-02-15 | 2021-02-15
47 | 71 | 2021-02-16 | 2021-02-16
48 | 72 | 2021-02-17 | 2021-02-17
49 | 73 | 2021-02-18 | 2021-02-18
50 | 74 | 2021-02-19 | 2021-02-19
51 | 75 | 2021-02-20 | 2021-02-20 | Third quarter ends
52 | 76 | 2021-02-21 | 2021-02-21
53 | 77 | 2021-02-22 | 2021-02-22
54 | 78 | 2021-02-23 | 2021-02-23
55 | 79 | 2021-02-24 | 2021-02-24
56 | 80 | 2021-02-25 | 2021-02-25
57 | 81 | 2021-02-26 | 2021-02-26
58 | 82 | 2021-02-27 | 2021-02-27
59 | 83 | 2021-02-28 | 2021-02-28
60 | 84 | 2021-03-01 | 2021-03-01
61 | 85 | 2021-03-02 | 2021-03-02
62 | 86 | 2021-03-03 | 2021-03-03
63 | 87 | 2021-03-04 | 2021-03-04
64 | 88 | 2021-03-05 | 2021-03-05
65 | 89 | 2021-03-06 | 2021-03-06
66 | 90 | 2021-03-07 | 2021-03-07
67 | 91 | 2021-03-08 | 2021-03-08
68 | 92 | 2021-03-09 | 2021-03-09
69 | 93 | 2021-03-10 | 2021-03-10
70 | 94 | 2021-03-11 | 2021-03-11
71 | 95 | 2021-03-12 | 2021-03-12
72 | 96 | 2021-03-13 | 2021-03-13
73 | 97 | 2021-03-14 | 2021-03-14
74 | 98 | 2021-03-15 | 2021-03-15
75 | 99 | 2021-03-16 | 2021-03-16
76 | 100 | 2021-03-17 | 2021-03-17 | End of first 100 days
77 |  | 2021-03-18 | 2021-03-18
78 |  | 2021-03-19 | 2021-03-19
79 |  | 2021-03-20 | 2021-03-20
80 |  | 2021-03-21 | 2021-03-21
81 |  | 2021-03-22 | 2021-03-22
82 |  | 2021-03-23 | 2021-03-23
83 |  | 2021-03-24 | 2021-03-24
84 |  | 2021-03-25 | 2021-03-25
85 |  | 2021-03-26 | 2021-03-26
86 |  | 2021-03-27 | 2021-03-27
87 |  | 2021-03-28 | 2021-03-28
88 |  | 2021-03-29 | 2021-03-29
89 |  | 2021-03-30 | 2021-03-30
90 |  | 2021-03-31 | 2021-03-31
91 |  | 2021-04-01 | 2021-04-01
92 |  | 2021-04-02 | 2021-04-02
93 |  | 2021-04-03 | 2021-04-03
94 |  | 2021-04-04 | 2021-04-04
95 |  | 2021-04-05 | 2021-04-05
96 |  | 2021-04-06 | 2021-04-06
97 |  | 2021-04-07 | 2021-04-07
98 |  | 2021-04-08 | 2021-04-08
99 |  | 2021-04-09 | 2021-04-09
100 |  | 2021-04-10 | 2021-04-10
Formulas:
Weekday = [Date]
Note on A1: Worth thinking about whether they want a true "first X days" system or if something with looser time restrictions is a better fit -Brendan Hellweg

## Committees
Number | Name | Priority | Icon 1 | Icon 2
1 | Building Public Safety | Reimagining Public Safety and Public Accountability
2 | Making Baltimore Equitable | Commit to Equity at the Core of City Services
3 | Prioritizing Our Youth | Expanding Opportunities for All of Baltimore's Youth
4 | Building Public Trust | Establishing Government Accountability from the Top Down
5 | COVID-19 Recovery | Leading an Effective Coronavirus Response for All
6 | Responsible Stewardship of City Resources | Aligning Resources to Ensure Fiscal Stability and Innovation

## Progress Updates
Update # | Date of Update | Description of Update
1 | 2020-12-14 | <p><span style="font-size: 16px;">Every week, our team will share updates from across our government to keep you involved in our work making Baltimore a safer, healthier, and more equitable city. Be sure to check back in to stay updated on our achievements during these hundred days and beyond!&nbsp;</span></p> <p><span style="font-size: 16px;">Since Mayor Scott took office on December 8th, 2020, we&rsquo;ve been hard at work improving Baltimore government. Below are a few highlights of Mayor Scott&rsquo;s achievements:</span></p> <ul> <li style="margin-left: 20px;"><span style="font-size: 16px;">Created and staffed the Mayor&rsquo;s Office of Neighborhood Safety and Engagement</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Launched the first PoliceStat meeting to coordinate services and increase accountability</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Hired Baltimore&rsquo;s first Chief Equity Officer</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Hired Baltimore&rsquo;s first Chief Administrative Officer</span></li> </ul> <p><span style="font-size: 16px;">We have bold plans to reshape Baltimore&rsquo;s government over the coming months. This work will involve unprecedented transparency, accountability, and urgency as we seek to build a Baltimore where every resident can thrive.</span></p> <p><br></p>

## Notes
This spreadsheet is designed to assist the Mayor's Office with tracking the set of short-term actions that it aims to accomplish within the first 100 days of Mayor Scott's term.
The Mayor's transition team has communicated to OPI that each of the 10 transition committees have been tasked with identifying 3-5 short-term actions to be accomplished within the first 100 days of the term. This means that in total, the committees will be identifying between 30-50 actions. Mayor Scott and his team will review this list and pare it down.
For each action, the following things should be determined:
Responsibility for completion of the action
Responsibility for communication of updates to the Mayor's team (and OPI for the purposes of the tracker)
Definition for what constitutes completion of the action
Project Timeline/Title:
100 Days of Action
Year 1 Agenda

## Possible Statuses
Status | Percentage
Incomplete
Complete

## Committees (old)
Number | Name | Priority | Icon 1 | Icon 2
1 | Public Health & Public Safety | Reimagining Public Safety and Public Accountability |  |  | Building Public Safety
2 | Business, Workforce & Neighborhood Development | Strengthening Neighborhoods and Businesses |  |  | Making Baltimore Equitable
3 | Fiscal Preparedness | Aligning Resources to Ensure Fiscal Stability and Innovation |  |  | Prioritizing Our Youth
4 | Education & Youth Recreation | Expanding Opportunities for Youth |  |  | Building Public Trust
5 | Housing & Neighborhood Development | Increasing Access to Affordable Housing |  |  | COVID-19 Recovery
6 | Transportation & Infrastructure | Reinvigorating Our Transportation and Infrastructure |  |  | Responsible Stewardship of City Resources
7 | Human Services | Prioritizing Our People
8 | Governance Structure & Operations | Rethinking Governmental Operations
9 | Environment & Sustainability | Protecting Natural Resources
10 | Arts & Culture | Valuing Creative Hubs and Cultural Institutions